## Company Margin
AMP Quality Energy Services — Company Margin (YTD Jan–Jun 2026)
From QBO P&L, accrual. The 40% target is a per-job GROSS margin floor; this shows where the company sits overall.
Line | Amount $ | % of Revenue
Revenue | 3398268 | 100%
Direct job cost (COGS) | -1362049 | -40.1%
Gross Profit | 2036220 | 59.9%
Overhead / Operating expense | -1679004 | -49.4%
Net Operating Income | 357215 | 10.5%
Other income / adj (net) | 142468 | 4.2%
Net Income | 499683 | 14.7%
Gross margin 60% (well above the 40% job floor); net operating only 10.5% — overhead is the drag. The job tracker flags individual jobs that fall below 40% gross.

## Job Scorecard
Job Scorecard — Are we ahead or behind the quote?
As of 2026-06-30. Gross margin vs 40% target. Green ≥40%, red <40%.
Metric | 26011 | 26061
Job # | 26011 | 26061
Title | DC Blox ATL-1B Tenant Fit Out | Test (8) sets of 13.8 kV Cables, June 18-19
Type | Multi-month | Short (multi-day)
Status | in_progress | ready_to_bill
Quoted $ | 1652107 | 24695
Billed $ | 922052 | 0
Collected $ | 720014 | 0
Open AR $ | 202038 | 0
— BUDGET vs ACTUAL —
Budget hours | 728 | 80.16
Actual hours | 2703.5167 | 92.6667
Hours variance % | 271.4% | 15.6%
— COST —
Labor (burdened) $ | 120496.04 | 3566.465
Other direct $ | 44450.54 | 1105.24
Cost to date $ | 164946.58 | 4671.705
— PROGRESS & PROJECTED MARGIN —
% complete (billed ÷ quote) | 55.81% | 100%
Projected total cost (EAC) $ | 295546.6714 | 4671.705
Projected gross margin % (at completion) | 82.11% | 81.08%
vs 40% target (projected) | ON TARGET | ON TARGET
— pace check —
Cost budget for 40% GM $ | 991264.2 | 14817
Expected cost @ % complete $ | 553231.2 | 14817
Cost-pace variance $ (actual − expected) | -388284.62 | -10145.295
GM % on billed-to-date (snapshot) | 82.11%

## 26011 Detail
26011 — DC Blox ATL-1B Tenant Fit Out
Multi-month · quote #4015 · status in_progress · as of 2026-06-30
Cost by category — Bid budget vs Actual
Category | Bid $ (where quoted) | Actual $ | Notes | Date | Cum Hours | Cum Labor $
Labor (W-2 + burden) |  | 120496.04 | 2704 actual hrs (budget 728 hrs) | 2026-02-02 | 23.1 | 60
Contract Labor |  | 20280.43 |  | 2026-02-03 | 24.3 | 60
Travel & Lodging | 15120 | 22220.37 | bid = travel labor + mileage | 2026-02-04 | 42.7 | 60
Per Diem / Meals | 0 | 14.73 |  | 2026-02-05 | 53.2 | 60
Materials | 0 | 1935.01 |  | 2026-02-06 | 77.7 | 80
Rental Equipment |  | 0 |  | 2026-02-09 | 107.2 | 735
Other |  | 0 |  | 2026-02-10 | 145.4 | 1664
TOTAL COST |  | 164946.58 |  | 2026-02-11 | 181.4 | 2482
|  |  |  | 2026-02-12 | 199.4 | 3100
MARGIN — projected at completion (not flattered by stage) |  |  |  | 2026-02-13 | 218.4 | 3752
Quoted (plan) | 1652107 |  |  | 2026-02-16 | 260.9 | 5584
Billed revenue | 922052 |  |  | 2026-02-17 | 298.2 | 6944
Collected | 720014 |  |  | 2026-02-18 | 309.7 | 7342
Cost to date | 164946.58 |  |  | 2026-02-19 | 321.2 | 7741
% complete (billed ÷ quote) | 55.81% |  |  | 2026-02-20 | 333.2 | 8156
Projected total cost (EAC) | 295546.6714 |  |  | 2026-02-21 | 342.2 | 8468
Projected gross margin % (at completion) | 82.11% |  |  | 2026-02-23 | 363.4 | 9173
Target | 40% |  |  | 2026-02-24 | 381.2 | 9792
Cost-pace variance (actual − expected @ %) | -388284.62 |  |  | 2026-02-25 | 408.2 | 10820
GM % on billed-to-date (snapshot only) | 82.11% |  |  | 2026-02-26 | 424.7 | 11360
|  |  |  | 2026-02-27 | 437.7 | 11785
|  |  |  | 2026-03-02 | 448.4 | 12079
|  |  |  | 2026-03-04 | 463.9 | 12814
|  |  |  | 2026-03-05 | 481.4 | 13329
|  |  |  | 2026-03-06 | 492.7 | 13636
|  |  |  | 2026-03-09 | 521.4 | 14524
|  |  |  | 2026-03-10 | 534.9 | 14913
|  |  |  | 2026-03-11 | 553.7 | 15488
|  |  |  | 2026-03-12 | 563.4 | 15755
|  |  |  | 2026-03-13 | 578.2 | 16240
|  |  |  | 2026-03-16 | 587.9 | 16572
|  |  |  | 2026-03-17 | 599.7 | 16967
|  |  |  | 2026-03-18 | 608.9 | 17283
|  |  |  | 2026-03-19 | 612.9 | 17409
|  |  |  | 2026-03-20 | 622.4 | 17738
|  |  |  | 2026-03-23 | 626.4 | 17889
|  |  |  | 2026-03-24 | 645.3 | 18597
|  |  |  | 2026-03-25 | 649.1 | 18742
|  |  |  | 2026-03-26 | 678.8 | 19829
|  |  |  | 2026-03-30 | 702.1 | 20608
|  |  |  | 2026-03-31 | 733.3 | 21667
|  |  |  | 2026-04-01 | 772.3 | 22919
|  |  |  | 2026-04-02 | 804.6 | 23937
|  |  |  | 2026-04-06 | 830.6 | 25174
|  |  |  | 2026-04-07 | 852.8 | 26094
|  |  |  | 2026-04-08 | 879.6 | 27380
|  |  |  | 2026-04-09 | 902.1 | 28286
|  |  |  | 2026-04-10 | 923.6 | 29010
|  |  |  | 2026-04-13 | 933.1 | 29330
|  |  |  | 2026-04-14 | 954.6 | 30055
|  |  |  | 2026-04-15 | 975.3 | 30754
|  |  |  | 2026-04-16 | 995.8 | 31445
|  |  |  | 2026-04-17 | 1026.8 | 32493
|  |  |  | 2026-04-20 | 1068.3 | 33879
|  |  |  | 2026-04-21 | 1108.8 | 35235
|  |  |  | 2026-04-22 | 1146.8 | 36506
|  |  |  | 2026-04-23 | 1164.8 | 37118
|  |  |  | 2026-04-27 | 1203 | 38352
|  |  |  | 2026-04-28 | 1237.5 | 39445
|  |  |  | 2026-04-29 | 1259.1 | 40079
|  |  |  | 2026-04-30 | 1294.6 | 41249
|  |  |  | 2026-05-01 | 1306.1 | 41623
|  |  |  | 2026-05-04 | 1330.3 | 42803
|  |  |  | 2026-05-05 | 1349.3 | 43426
|  |  |  | 2026-05-06 | 1393 | 45763
|  |  |  | 2026-05-07 | 1439.5 | 48178
|  |  |  | 2026-05-08 | 1469 | 49164
|  |  |  | 2026-05-11 | 1507 | 50862
|  |  |  | 2026-05-12 | 1545 | 52560
|  |  |  | 2026-05-13 | 1594.8 | 54946
|  |  |  | 2026-05-14 | 1642.3 | 57460
|  |  |  | 2026-05-15 | 1712 | 61064
|  |  |  | 2026-05-16 | 1781 | 64514
|  |  |  | 2026-05-18 | 1845.3 | 67621
|  |  |  | 2026-05-19 | 1909 | 70104
|  |  |  | 2026-05-20 | 1953.3 | 71829
|  |  |  | 2026-05-21 | 2001 | 73904
|  |  |  | 2026-05-22 | 2034 | 75224
|  |  |  | 2026-05-26 | 2073.5 | 76934
|  |  |  | 2026-05-27 | 2128.5 | 79345
|  |  |  | 2026-05-28 | 2185.3 | 82046
|  |  |  | 2026-05-29 | 2228.3 | 84065
|  |  |  | 2026-06-01 | 2282.3 | 86553
|  |  |  | 2026-06-02 | 2319.3 | 88170
|  |  |  | 2026-06-03 | 2336.8 | 88880
|  |  |  | 2026-06-04 | 2356.8 | 89789
|  |  |  | 2026-06-05 | 2381.8 | 90880
|  |  |  | 2026-06-08 | 2409.5 | 92065
|  |  |  | 2026-06-09 | 2454 | 94243
|  |  |  | 2026-06-10 | 2494.5 | 96111
|  |  |  | 2026-06-11 | 2531.5 | 97622
|  |  |  | 2026-06-12 | 2553.3 | 98558
|  |  |  | 2026-06-15 | 2572.8 | 99468
|  |  |  | 2026-06-16 | 2586.3 | 100130
|  |  |  | 2026-06-17 | 2596.3 | 100471
|  |  |  | 2026-06-18 | 2605.8 | 100795
|  |  |  | 2026-06-19 | 2617.3 | 101187
|  |  |  | 2026-06-22 | 2635.8 | 101935
|  |  |  | 2026-06-23 | 2662.8 | 103060
|  |  |  | 2026-06-24 | 2690.8 | 104219
|  |  |  | 2026-06-25 | 2696 | 104385
|  |  |  | 2026-06-26 | 2703.5 | 104623

## 26061 Detail
26061 — Test (8) sets of 13.8 kV Cables, June 18-19
Short (multi-day) · quote #4224 · status ready_to_bill · as of 2026-06-30
Cost by category — Bid budget vs Actual
Category | Bid $ (where quoted) | Actual $ | Notes | Date | Cum Hours | Cum Labor $
Labor (W-2 + burden) |  | 3566.465 | 93 actual hrs (budget 80 hrs) | 2026-06-16 | 2 | 95
Contract Labor |  | 675.75 |  | 2026-06-18 | 62 | 2360
Travel & Lodging | 4286.4 | 418.29 | bid = travel labor + mileage | 2026-06-19 | 89.7 | 3425
Per Diem / Meals | 130 | 11.2 |  | 2026-06-22 | 92.7 | 3566
Materials | 0 | 0
Rental Equipment |  | 0
Other |  | 0
TOTAL COST |  | 4671.705
MARGIN — projected at completion (not flattered by stage)
Quoted (plan) | 24695
Billed revenue | 0
Collected | 0
Cost to date | 4671.705
% complete (billed ÷ quote) | 100%
Projected total cost (EAC) | 4671.705
Projected gross margin % (at completion) | 81.08%
Target | 40%
Cost-pace variance (actual − expected @ %) | -10145.295
GM % on billed-to-date (snapshot only)