# AMP Job Profitability Tracker — Integration Guide

Prepared for: Jack (ampOS) — to integrate native job-profitability tracking into ampOS

Prepared by: Jeremy Smith (Fractional CFO), with build support

Date: 2026-06-30

Status: Working reference implementation complete; this document is the spec to rebuild it natively in ampOS.

────────

## 1. What this is and why

A live "are we ahead or behind the quote?" tracker for every AMP (AMPQES) job. For each job it compares, by cost category:

The QUOTE / budget — what was bid (from ampOS estimates)

The ACTUALS to date — real revenue, cost, and to-the-day labor hours (from QuickBooks)

…and reports gross margin vs the 40% target, projected to completion (so an early-stage job isn't flattered), with click-any-number drill-down to the underlying records.

A fully working reference implementation exists today (Python + a self-contained HTML dashboard, refreshed daily). This guide gives you everything to rebuild it *inside* ampOS, where the bid data already lives and only the QuickBooks actuals need to be brought in.

The headline business goal: watch gross margin, target 40%, and catch jobs trending below it while they're still running.

────────

## 2. Architecture / data flow

`

ampOS (Supabase)                         QuickBooks Online (AMPQES)

─────────────────                        ──────────────────────────

business.opportunities  ┐               Customer (Job=true sub-customers)

business.estimates      │  BID/BUDGET    TimeActivity   (to-the-day hours + cost rate)

neta_ops.jobs           │                Invoice        (billed / collected)

common.customers        ┘                ProfitAndLossDetail by customer (cost by account)

│                                          │

└──────────────┬───────────────────────────┘

│  JOIN on job number

▼

Per-job profitability model

(budget vs actual by category, EAC margin)

│

▼

Dashboard UI (per job)

`

The whole trick is the join: an ampOS job number (e.g. 26011) equals the prefix of the QBO sub-customer name (26011 - DC Blox ATL-1B Tenant Fit Out). See §4.

For ampOS, the bid side is already in your database. The integration work is: (a) bring in the QBO actuals keyed by job, (b) implement the calculations in §5–6, (c) build the UI in §7.

### 2.1 Native (your) access vs. the reference's external access — important

The reference implementation reaches ampOS from outside (anon key + a user access token minted from a Supabase refresh token + the Accept-Profile header). You do not need any of that. You are inside ampOS: the quote/bid tables (business.opportunities, business.estimates, neta_ops.jobs) are your own database — query them directly with your normal server/Supabase privileges. The quote data does NOT need to be re-sourced through the external API; it already works for you.

So from your side:

Quote/budget side → already native. Reuse the field map and JSON shapes in §3 and the formulas in §6.1; ignore ampos_auth.py / pull_ampos.py (those exist only so an external tool could read your DB).

Actuals side → the real new build. QuickBooks data is not in ampOS today. Sync TimeActivity / Invoice / ProfitAndLossDetail per job (§11, step 2).

Bottom line: the only genuinely new data integration is QuickBooks. Everything on the quote side is reading tables you already own.

────────

## 3. Data sources & fields

### 3.1 ampOS (Supabase project `vdxprdihmbqomwqfldpo`)

PostgREST exposes multiple Postgres schemas; set the schema per request with the Accept-Profile header (REST) or db.schema (supabase-js). You already own this data — listed here so the field semantics are unambiguous.

| Table | Schema | Fields used | Notes |
| --- | --- | --- | --- |
| opportunities | business | id, quote_number, title, quoted_amount, total_man_hours, status, opportunity_type, amp_division, customer_id, contact_id, job_id, awarded_date, prepared_by, probability | The bid. `quoted_amount` is the authoritative bid revenue. status: awareness/interest/quote/decision/awarded/lost/no quote. opportunity_type: large_acceptance/small_acceptance/maintenance/engineering/time_materials/other. |
| estimates | business | id, opportunity_id, status, created_at, data (JSONB), travel_data | The quote breakdown lives in `data` (see §3.3). Use the latest estimate per opportunity (ORDER BY created_at DESC). |
| jobs | neta_ops | id, job_number, title, budget, estimated_man_hours, opportunity_id, status, division, customer_id, quickbooks_project_id, quickbooks_project_name | The won/active job. `opportunity_id` links back to the bid. status: pending/in_progress/ready_to_bill/progress_billing/billed/completed/cancelled. `quickbooks_project_id` / `_name` exist but are currently EMPTY — see §4 recommendation. |
| customers | common | id, name, company_name | For display names. |
| contacts | common | id, customer_id, first_name, last_name, email | Optional. |

### 3.2 Important: `estimates.data.calculatedValues` is UNRELIABLE for dollars

The estimate JSON stores a calculatedValues block whose grandTotal / labor figures do not reconcile with the actual quoted price (they store labor hours in a labor-$ field, etc. — see the existing "Estimator Labor Bug" memo). Do not use it for money. Use opportunities.quoted_amount for revenue and derive budget cost from the line items + hours (§6.1).

### 3.3 `estimates.data` (JSONB) — the quote breakdown

`jsonc

{

"sovItems": [                       // scope-of-value line items

{ "item": "Low Voltage Panelboard PDP", "quantity": 1,

"materialPrice": 0, "expensePrice": 0,

"laborMen": 2, "laborHours": 3, "notes": "PDP-J/1" }

],

"hoursSummary": {                    // labor hours roll-up (RELIABLE)

"men": 2, "hoursPerDay": 8, "daysOnsite": 6.3,

"workHours": 64,        // onsite SOV labor hours

"nonSovHours": 4,

"travelHours": 12.16,

"totalHours": 80.16,

"straightTimeHours": 50.6, "overtimeHours": 0, "doubleTimeHours": 0

},

"travel_data": {

"travelExpense": [ { "trips": 5, "totalMiles": 250, "rate": 3, "vehicleTravelCost": 750 } ],   // mileage cost

"travelTime":   [ { "grandTotalTravelHours": 10, "rate": 240, "totalTravelLabor": 2400 } ],     // travel labor

"perDiem":      [ { "numDays": 0, "firstDayRate": 65 } ]

},

"hourlyRates": { "straightTime": 240, "overtime": 360, "doubleTime": 480 },   // BILLING rate, not cost

"mobilizationFactors": { "base": 0, "over100k": 0.10, "over500k": 0.05, "over1m": 0.05 },

"paymentTermFactors":  { "net30": 1, "net60": 1.06, "net90": 1.09 },

"materialMarkup": 0

}

`

Note hourlyRates (ST $240) is the billing rate used to price the quote — it is not labor cost. Actual labor cost comes from QBO (§3.4).

### 3.4 QuickBooks Online (AMPQES — realm `123145887114114`, Accounting API, read-only)

| Entity | Fields used | Purpose |
| --- | --- | --- |
| Customer (where Job=true) | Id, DisplayName, FullyQualifiedName | Jobs are sub-customers named "<jobnumber> - <title>". The join key. |
| TimeActivity | TxnDate, EmployeeRef, CustomerRef, Hours, Minutes, CostRate, Description | To-the-day labor hours and cost. Labor cost = Hours × CostRate. ~51,800 rows company-wide. |
| Invoice | TxnDate, DocNumber, TotalAmt, Balance, CustomerRef | Billed (TotalAmt) and collected (TotalAmt − Balance) revenue per job. |
| ProfitAndLossDetail report, customer=<Id>, accounting_method=Accrual | rows by account | Authoritative job cost by category (materials, travel, per diem, and job-costed wages where present). |

### 3.5 QuickBooks connection — the ONE credential you must set up (where the token goes)

This is the only token you need to add. The ampOS/quote side is native (no token — see §2.1); QuickBooks is the one external system.

Do not reuse the reference's QuickBooks access. The reference reads QBO through Jeremy's shared CLI (AI\QBO\qbo.js --client ampqes) with his OAuth app and tokens in ~/.qbo-tokens/.env. That is Jeremy's personal external setup — not what ampOS uses. ampOS needs its own server-side QBO connection.

Set up an OAuth2 connection from the ampOS backend to the AMPQES QuickBooks company:

App credentials (Client ID + Secret). Use AMP's existing Intuit Developer app if there is one, otherwise create one at developer.intuit.com (Production keys). Store the Client ID/Secret as backend secrets (env vars / secret manager) — e.g. QBO_CLIENT_ID, QBO_CLIENT_SECRET. Never in client-side code.

Scope: com.intuit.quickbooks.accounting (read-only is sufficient for this tool).

Company / realm: AMPQES = realm `123145887114114`. An AMPQES QuickBooks admin authorizes once via the OAuth2 consent flow; the callback returns the realmId + an authorization code you exchange for tokens.

Tokens (this is "where the token goes"): the exchange returns an access token (~1 hour) and a refresh token (~100 days, rotates on each use). Store both server-side (a secrets table / secure config keyed by realm), refresh the access token on demand, and persist the rotated refresh token each time (same pattern as the ampOS refresh-token flow in ampos_auth.py, and as Jeremy's qbo.js does). If the refresh token ever expires/revokes, an admin re-authorizes.

Then call the Accounting API (/v3/company/123145887114114/query and the …/reports/ProfitAndLossDetail endpoint) with Authorization: Bearer <access token> — the exact queries are in §12.

So: one token to wire up (QuickBooks), stored and refreshed in the ampOS backend. The quote/bid side needs none.

QBO COGS / job-cost accounts (from the AMPQES chart of accounts):

| Account | Category |
| --- | --- |
| 5006 Direct Cost – Wages, 5030 Direct Cost – Payroll, 6003 Taxes, 6010 Retirement Co Match | Labor (W-2 + burden) |
| 5008 Direct Cost – Contract Labor | Contract Labor |
| 5004 Direct Cost – Travel & Lodging | Travel & Lodging |
| 5002 Direct Cost – Fuel | Fuel / Mileage |
| 6390 Per Diem, 6270 Meals & Entertainment 50%, 5003 Meals | Per Diem / Meals |
| 5001 Direct Cost – Job Materials | Materials |
| 5007 Direct Cost – Rental Equipment | Rental Equipment |
| 5009 Third Party Testing, 5005 Postage, 5050 Insurance | Other |

────────

## 4. The join (ampOS job ↔ QBO actuals) — and the one fix that makes it bulletproof

Today: match jobs.job_number to the leading number of the QBO sub-customer DisplayName:

regexp '^\s*(\d{5})' → that 5-digit job number → Customer.Id. This matched 132 of 145 jobs; the other 13 had naming differences (no number, typos, or not yet created in QBO).

Recommended permanent fix (high value, low effort):

Populate `neta_ops.jobs.quickbooks_project_id` (and `_name`) with the QBO sub-customer / Project Id when a job is created or converted from an opportunity. The columns already exist and are empty. Once populated, the join is an exact foreign key instead of fragile name-matching, and the 13 unmatched jobs disappear. This is the single most valuable integration step.

QBO also exposes a native Projects feature (ProjectRef on TimeActivity, e.g. 587957375); either the sub-customer Id or the Project Id can be stored — be consistent.

────────

## 5. Methodology (confirmed with Jeremy)

Primary KPI: per-job GROSS MARGIN = (Revenue − fully-burdened direct cost) ÷ Revenue. Target = 40% (a floor). Flag any job whose projected gross margin is below 40%.

Secondary: net margin after overhead, allocating company overhead at % of revenue (see §6.4).

Progress / "ahead or behind" is projected to completion using billing % complete so in-progress jobs aren't flattered (see §6.3).

Company context (AMPQES YTD Jan–Jun 2026, from QBO P&L): Revenue $3,398,268 · COGS $1,362,049 → gross 59.9% · OpEx $1,679,004 → net operating 10.5%. So 40% is a per-job gross floor; the company runs well above it at gross but overhead is the drag on net. The tracker's job is to surface the individual jobs that erode the gross.

────────

## 6. Calculations (the heart — implement exactly)

### 6.1 Budget (quote) side — per job

From the latest estimate's data:

`

realized_rate   = actual_labor_cost / actual_worked_hours   # job's own QBO cost/hr (see 6.2); fallback ~$45

budget_labor    = (workHours + nonSovHours) * realized_rate

budget_travel   = travelHours * realized_rate  +  Σ travel_data.travelExpense[].vehicleTravelCost

budget_perdiem  = Σ travel_data.perDiem[].numDays * firstDayRate

budget_material = Σ sovItems[].quantity * materialPrice

budget_COGS     = budget_labor + budget_travel + budget_perdiem + budget_material

budget_revenue  = opportunities.quoted_amount

budget_GM%      = (budget_revenue − budget_COGS) / budget_revenue

`

Valuing budget labor at the job's realized cost rate makes budget-vs-actual labor a clean hours comparison. (Alternatively use a fixed company loaded rate; just be explicit.)

### 6.2 Actual side — per job

`

# Revenue

billed     = Σ Invoice.TotalAmt        (CustomerRef = job)

collected  = Σ (Invoice.TotalAmt − Invoice.Balance)

# Labor (to-the-day) from TimeActivity

worked_hours    = Σ Hours  where CostRate > 0        # exclude $0-rate per-diem markers (see §8)

labor_TimeAct   = Σ Hours * CostRate

labor_PNL       = Σ ProfitAndLossDetail amount in accounts {5006,5030,6003,6010}

actual_labor    = max(labor_PNL, labor_TimeAct)      # see double-count rule below

# Non-labor actual cost by category, from ProfitAndLossDetail (EXCLUDING the labor accounts above)

actual_other    = Σ P&L expense rows grouped by category map in §3.4

actual_COGS     = actual_labor + actual_other

`

Double-count rule (critical): some jobs have wages job-costed in the P&L (account 5006 present) and some do not (wages not tagged to the sub-customer). To get a consistent, complete labor figure without double counting:

Take labor = `max(P&L labor accounts, TimeActivity Hours×CostRate)`.

Build non-labor cost from the P&L *excluding* accounts 5006/5030/6003/6010 (so labor is never counted twice).

Always use TimeActivity for hours (and for the daily/monthly curve).

### 6.3 Projected margin at completion (EAC) — "ahead or behind"

`

pct_complete = 1.0                              if status ∈ {billed, ready_to_bill, completed, progress_billing}

= min(billed / quoted_amount, 1)   elif billed > 0

= null                             else  (in-progress, nothing billed → cannot project)

proj_total_cost = actual_COGS / pct_complete

proj_GM%        = (quoted_amount − proj_total_cost) / quoted_amount     # <-- compare THIS to 40%

# pace check (is cost outrunning the margin budget right now?)

cost_budget_for_40 = quoted_amount * (1 − 0.40)

expected_cost_now  = cost_budget_for_40 * pct_complete

cost_pace_variance = actual_COGS − expected_cost_now     # +ve = over budget pace (margin eroding)

`

Do not compare cost-to-date against the full quote — that flatters early-stage jobs (a known trap; this is why EAC exists). Caveat: billing-% EAC assumes cost and billing move together; if a job is front-loaded on billing it under-states final cost — cross-check with report-completion % (§10).

### 6.4 Net margin after overhead (secondary)

`

overhead_rate = company_OpEx / company_revenue        # ≈ 0.494 YTD

net_margin%   = proj_GM% − overhead_rate

`

────────

## 7. Dashboard UI spec

One job at a time. Searchable job picker (click → list all jobs with status; type → filter). Active jobs (in_progress / ready_to_bill / progress_billing) sorted first.

Summary (top): Status · Quoted · Billed · Collected · % complete · Budget COGS · Actual COGS · Projected final cost · Budget GM% · Projected GM% (flagged green ≥40% / red <40%) · Hours budget→actual · Net margin after overhead.

Quote (left) and Actuals (right): same category rows — Revenue, then COGS by category (Labor, Contract Labor, Travel & Lodging, Fuel/Mileage, Per Diem/Meals, Materials, Rental Equipment, Other), then Total COGS and Gross margin %.

Monthly view (bottom): cost (incurred) vs billed, by month — reveals front-loaded billing and burn pace.

Drill-down: every number is clickable to the underlying records:

Quote numbers → estimate SOV line items / travel_data.

Actual labor → TimeActivity rows (date, employee, hours, cost rate, cost).

Actual cost categories → the ProfitAndLossDetail transactions in that category.

Actual revenue → invoices.

Monthly bar → that month's transactions + time.

The reference HTML (AMP Job Dashboard.html) implements all of this; open it to see the exact behavior and styling.

────────

## 8. Reference implementation (included in this package)

A runnable Python pipeline that produces the dashboard. Use it to validate your native build against known-good numbers.

| File | What it does |
| --- | --- |
| ampos_auth.py | Unattended ampOS auth via Supabase refresh token (stored outside OneDrive, auto-rotated). |
| pull_ampos.py | Pulls the 5 ampOS tables → data/*.json. |
| pull_all_qbo.py | Maps every job to its QBO sub-customer; pulls TimeActivity / Invoice / P&L-detail per job (node qbo.js). |
| qbo_load.py | Parsers + roll-ups for the QBO JSON (TimeActivity, P&L detail, invoices). |
| build_dashboard.py | Builds AMP Job Dashboard.html (all calcs in §6, the UI in §7). This is the executable spec. |
| build_all.py | Orchestrates a full daily refresh (ampOS → map → QBO → HTML). |
| build_model.py, build_tracker_prototype.py | Excel versions (overview model + per-job tracker prototype). |

QBO access uses the shared CLI at …\FocusCFO\AI\QBO\qbo.js (--client ampqes), Accounting scope, read-only. ampOS access uses the anon key (public, baked in the app) + a user access token minted from the refresh token.

### Quickstart (reproduce the reference)

`

# QBO tokens already configured for ampqes in ~/.qbo-tokens/.env

python ampos_auth.py seed <refresh_token_from_browser_localStorage>   # one-time

python pull_ampos.py        # ampOS bid data

python pull_all_qbo.py      # QBO actuals (a few minutes)

python build_dashboard.py   # -> AMP Job Dashboard.html

# or just: python build_all.py

`

────────

## 9. Automation / refresh (reference implementation)

Cadence: once daily is correct (QBO posts over hours/days).

build_all.py refreshes ampOS, remaps new jobs, re-pulls active jobs' actuals (completed jobs stay cached), and regenerates the HTML.

Scheduled via Windows Task Scheduler ("AMP Job Dashboard", 6:00 AM) → refresh_dashboard.bat → refresh.log.

Tokens auto-refresh (QBO via qbo.js; ampOS via ampos_auth.py), so it runs unattended.

In a native ampOS build you'd replace the daily file pull with a QBO sync job writing actuals into your own tables (see §11).

────────

## 10. Data-quality findings & caveats (read before trusting numbers)

`estimates.data.calculatedValues` is wrong for dollars — use quoted_amount + line items (§3.2). Worth fixing the estimator so the stored totals are correct.

Per-diem time entries inflate hours. Many TimeActivity rows are per-diem/day markers; some carry $0 CostRate. Count worked hours as `CostRate > 0` (labor cost is already correct since $0-rate rows add nothing). Even so, techs annotate real paid hours "Per diem", so don't filter on the description.

Revenue isn't always tagged to the job sub-customer. Some jobs show cost but $0 invoices (billed via parent, or not yet invoiced). Always compare against the quote, not just billed.

Billing is often front-loaded (invoice ahead of cost) — the monthly view shows this; it makes billing-% EAC optimistic. Consider an ampOS-native report-completion % (jobs already track report counts, e.g. 173 of 279 sent) as an independent progress signal and cross-check.

`amp_division` values are inconsistent (Alabama vs north_alabama, etc.) — normalize.

13 of 145 jobs didn't match QBO by name — fixed permanently by populating quickbooks_project_id (§4).

40% is a *gross* (direct-cost) floor, not net. Jobs commonly run 60–90% gross; the value is catching the low ones and watching the company roll-up vs overhead.

────────

## 11. Recommended native-ampOS integration plan (for Jack)

Bind jobs to QBO — populate jobs.quickbooks_project_id/_name on job creation/conversion (§4). Backfill existing jobs once (the name-match map in the reference covers 132/145; finish the rest by hand).

Add a QBO sync (ampOS already has Supabase + a backend) — set up the server-side QuickBooks OAuth connection per §3.5 (the one token to wire up), then on a daily job pull per active job fetch: TimeActivity, Invoice, and ProfitAndLossDetail (customer=…). Store into new tables, e.g. neta_ops.qbo_time, qbo_invoice, qbo_job_cost (account, category, amount, date). Keep completed jobs cached.

Implement the calc (§6) as a view/service: job_profitability(job_id) returning budget-by-category, actual-by-category, EAC, margins.

Build the UI (§7) as a "Profitability" tab on the existing Job page — quote vs actual table, summary, monthly chart, and drill-downs (you already have the estimate data; the QBO rows come from step 2).

Surface the 40% flag on job lists / the sales dashboard so leakers are visible at a glance.

(Optional) Fix the estimator calculatedValues bug (§10.1) so the quote's stored cost/margin are correct natively.

Minimum viable version: steps 1–4 for active jobs only. Everything needed is in this document and the reference code.

────────

## 12. Appendix — exact queries

ampOS (PostgREST, header `Accept-Profile: <schema>`):

`

business: GET /rest/v1/opportunities?select=*&limit=10000

business: GET /rest/v1/estimates?select=id,opportunity_id,quote_number,status,created_at,data,travel_data

neta_ops: GET /rest/v1/jobs?select=*&deleted_at=is.null

common:   GET /rest/v1/customers?select=id,name,company_name

`

QBO (Accounting API / `qbo.js`):

`

query:  SELECT Id, DisplayName FROM Customer WHERE Job=true

query:  SELECT * FROM TimeActivity WHERE CustomerRef='<id>'

query:  SELECT * FROM Invoice      WHERE CustomerRef='<id>'

report: ProfitAndLossDetail customer=<id> accounting_method=Accrual start_date=YYYY-01-01 end_date=YYYY-12-31

report: ProfitAndLoss start_date=… end_date=… accounting_method=Accrual   (company roll-up / overhead rate)

`

QBO query quirks: TimeActivity has no ORDER BY; no OR / multi-LIKE; Purchase is not filterable by CustomerRef (use the P&L detail report for cost).

────────

Reference implementation, this guide, the Excel models, and a sample of the live dashboard are included in the Handoff to Jack package. Questions → Jeremy.